## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
Airline Reservation System | 1 | Analysis | Requirement Analysis | 1 | 2017-10-18 | 2017-10-18 | 1 | 2017-03-03 | 2017-03-03 |  | Completed
|  |  | Preparing understanding document | 1 | 2017-10-18 | 2017-10-18 | 1 | 2017-03-03 | 2017-03-03 | Sai Eshwar Myneni | Completed
|  |  | Updating QTS | 1 | 2017-10-18 | 2017-10-18 | 0.5 | 2017-03-03 | 2017-03-03 | Abhishek Goyal | Completed
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2017-10-18 | 2017-10-19 | 2 | 2017-03-03 | 2017-03-03 | Sai Eshwar Myneni, Abhishek Goyal, Bhava Sagar,Sneha | Completed
|  | Design | Unit Test Plan Preparation | 1 |  |  | 1.5
|  |  | LLD Preparation | 3 |  |  | 3 |  |  | Sai Eshwar Myneni
|  |  | UTP Review | 0.5 |  |  | 0.5
|  |  | UTP Rework | 1 |  |  | 1
|  |  | LLD Review | 1 |  |  | 1
|  | Build | Coding | 6 |  |  | 6
|  |  | Code Self Review | 3 |  |  | 3
|  |  | Self Testing | 2 |  |  | 2
|  |  | Rework | 3 |  |  | 3
|  |  | Code Peer Review | 4 |  |  | 4
|  |  | Peer Testing | 5 |  |  | 5
|  |  | Test Result review | 2 |  |  | 2
|  |  | Rework | 1 |  |  | 1
|  |  | Code Integration | 2 |  |  | 2 |  |  | Sai Eshwar Myneni
|  |  | Integration Testing | 1 |  |  | 1 |  |  | Abhishek Goyal
|  |  | Rework | 1 |  |  | 1 |  |  | Rohit Agrawal
|  |  | Test Result review | 1 |  |  | 1
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: | 41.5